## README
UK Government Major Projects
Cost, Schedule and Delivery-Risk Dashboard
Portfolio analysis of the 2024–25 and 2025–26 NISTA Major Projects datasets
This workbook analyses major UK government projects by department, whole-life cost, schedule duration and delivery-confidence rating. It combines multiple annual datasets through Power Query, models the portfolio in Power Pivot and applies a custom analytical risk score to support project-level prioritisation.
Worksheet | Purpose
Executive Dashboard | Headline portfolio KPIs and year comparison
Departmental Analysis | Department cost and delivery-risk comparison
Project Risk Register | Sortable project-level analytical risk register
Risk Summary | Risk-tier distribution and cost exposure
Data Quality | Record-count validation and data-completeness checks
Methodology | Data preparation, scoring rules and limitations
README | Workbook instructions and project overview
Refresh instructions
1. Store the annual source CSV files in the designated source-data folder.
2. Do not manually edit the source CSV files.
3. Open the workbook and select Data → Refresh All.
4. Confirm the Data Quality page shows 213 records for 2024–25 and 189 records for 2025–26.
5. Check that dashboard slicers and PivotTables update successfully
6.Portfolio viewers can use the cached workbook outputs without the source CSV files; refreshing requires the annual source files in the established source-data folder.
Technical features demonstrated
1.Power Query for importing, cleaning, standardising and appending annual datasets
2.Power Pivot relationships between fact and dimension tables
3.DAX measures for project counts, portfolio cost, duration and rating distribution
4.Custom 100-point analytical project-risk methodology
5.PivotTables, PivotCharts, slicers and conditional formatting
6.Refreshable project-level risk register
*DISCLAIMER
The Analytical Risk Score is independently developed for portfolio analysis. It is not an official NISTA, IPA or departmental assessment. High cost and long duration represent exposure and complexity, not necessarily poor project management.
Workbook Details
Item | Value
Author | Wajedul Haque
Tool | Microsoft Excel 365
Reporting years | 2024–25 and 2025–26
Source unit | £ millions in 2024–25 real prices
Data refresh | Power Query
Model | Power Pivot and DAX
Version | 1

## Executive Dashboard
UK Government Major Projects Cost, Schedule and Delivery-Risk Dashboard
Project Records | Average Duration Months | Red or Amber % of Rated Projects | Total Whole Life Cost £bn
167 | 148.9274 | 93.41% | 656.7525
Portfolio reported at 31 March 2026 ¦ Costs presented in 2024–25 real prices
Analytical Risk Score is independently developed and is not an official government project rating.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Pivot Support
Row Labels | Project Records | Row Labels | Total Whole Life Cost £bn | Project Name | Total Risk Score | Department | GREEN | AMBER | RED
AMBER | 112 | 2024-25 | 336.5835 | ARMOURED CAVALRY 2025 | 100 | MOD | 1 | 10 | 9
GREEN | 11 | 2025-26 | 320.169 | ARMOUR MBT 2025 | 95 | DFT | 0 | 3 | 3
RED | 44 | Grand Total | 656.7525 | FARMING AND COUNTRYSIDE PROGRAMME | 90 | HO | 0 | 6 | 2
|  |  |  | Remediation Portfolio | 90 | DESNZ | 0 | 4 | 3
|  |  |  | EAST COAST DIGITAL PROGRAMME | 90 | DHSC | 1 | 2 | 0
|  |  |  | SUBMARINE WATERFRONT INFRASTRUCTURE FUTURE | 90 | DEFRA | 2 | 4 | 2
|  |  |  | NEW HOSPITAL PROGRAMME | 85 | MHCLG | 0 | 2 | 1
|  |  |  | NORTHERN POWERHOUSE RAIL | 85 | DFE | 1 | 0 | 0
|  |  |  | Hydrogen Allocation Round 2 (HAR2) | 85 | DWP | 1 | 5 | 0
|  |  |  | LAND ENVIRONMENT TACTICAL COMMUNICATION AND INFORMATION SYSTEMS | 85 | MOJ | 0 | 5 | 2
|  |  |  | MECHANISED INFANTRY PROGRAMME | 85
|  |  |  | NEW STYLE OF INFORMATION TECHNOLOGY DEPLOYED | 85
|  |  |  | GEOLOGICAL DISPOSAL FACILITY | 80
|  |  |  | COLLECTIVE TRAINING TRANSFORMATION PROGRAMME | 80
|  |  |  | LAND INTELLIGENCE, SURVEILLANCE, TARGET ACQUISITION AND RECONNAISSANCE (ISTAR) | 80
|  |  |  | GROUND BASED AIR DEFENCE (GBAD) | 80
|  |  |  | Law Enforcement Data Service | 80
|  |  |  | CORE PRODUCTION CAPABILITY | 75
|  |  |  | COLLECTIONS, PACKAGING AND REFORMS PROGRAMME | 75
|  |  |  | FUTURE BORDER AND IMMIGRATION SYSTEM PROGRAMME (FBIS) | 75
|  |  |  | SERVICE MODERNISATION PROGRAMME | 75
|  |  |  | FUTURE AIR DOMINANCE SYSTEM | 75
|  |  |  | 10K Additional Prison Places Estate Expansion Houseblocks and Refurbishments | 75
|  |  |  | 10K Additional Prison Places Estate Expansion Category D | 75
|  |  |  | LOWER THAMES CROSSING | 70
|  |  |  | Workplace Transformation | 70
|  |  |  | CLYDE INFRASTRUCTURE | 70
|  |  |  | HOME OFFICE BIOMETRICS (HOB) PROGRAMME | 70
|  |  |  | MAKING TAX DIGITAL | 70
|  |  |  | Health Transformation Programme | 70
|  |  |  | Warm Homes Agency | 70
|  |  |  | UNITY PROGRAMME | 70
|  |  |  | EMERGENCY SERVICES MOBILE COMMUNICATIONS | 65
|  |  |  | Affordable Homes Programme (AHP) | 65
|  |  |  | SOCIAL HOUSING DECARBONISATION FUND | 65
|  |  |  | FRONTLINE DIGITISATION | 65
|  |  |  | SYNERGY PROGRAMME | 65
|  |  |  | Electronic Monitoring Expansion | 65
|  |  |  | National Biosecurity Centre (Weybridge) | 60
|  |  |  | Manchester Digital Campus | 60
|  |  |  | GOV.UK One Login | 60
|  |  |  | Livestock Information Transformation Programme | 60
|  |  |  | Warm Homes: Local Grant | 60
|  |  |  | Enterprise Customer Relationship Management (eCRM) | 60
|  |  |  | 4th National Lottery Licence | 60
|  |  |  | SKYNET 6 (AKA FBLOS) | 60
|  |  |  | TYPE 31 | 60
|  |  |  | Flood and Coastal Risk Management (FCRM) Investment Programme 2026-2029 | 55
|  |  |  | POST OFFICE - TRANSFORMATION | 55
|  |  |  | EU Delivery Programme | 55
|  |  |  | Contact Centre as a Service (CCaaS) | 55
|  |  |  | VOA NextGen Rating Programme | 55
|  |  |  | NEXT GENERATION (FIXED) COMMUNICATION NETWORK | 55
|  |  |  | Small Secure Houseblocks | 55
|  |  |  | Rapid Deployment Cells Project | 55
|  |  |  | Accelerated Houseblocks | 55
|  |  |  | MENSA | 50
|  |  |  | MODNET EVOLVE | 50
|  |  |  | Police National Database (PND) | 50
|  |  |  | Spherical Tokamak for Energy Production | 50
|  |  |  | PENSIONS DASHBOARD PROGRAMME | 50
|  |  |  | 10k Additional Prison Places - New Build | 50
|  |  |  | FLOOD AND COASTAL EROSION RISK MANAGEMENT | 45
|  |  |  | NATURE FOR CLIMATE FUND | 45
|  |  |  | EURO 2028 | 45
|  |  |  | ASYLUM TRANSFORMATION PROGRAMME | 45
|  |  |  | PUBLIC OWNERSHIP TRANSITION PROGRAMME | 45
|  |  |  | SUBMERSIBLE SHIP NUCLEAR AUKUS | 45
|  |  |  | FUTURE COMBAT AIR SYSTEM | 45
|  |  |  | HS2 PHASE I | 40
|  |  |  | Rail Reform: Stand-Up of GBR | 40
|  |  |  | NS&I Transformation | 40
|  |  |  | Asylum Support Accommodation Programme | 40
|  |  |  | ASYLUM ACCOMMODATION PROGRAMME (AAP) | 40
|  |  |  | DIGITAL PLANNING PROGRAMME | 35
|  |  |  | INTEGRATED SINGLE FINANCIAL ENVIRONMENT | 35
|  |  |  | Early Years Childcare Reform Programme | 30
|  |  |  | Connect to Work | 30
|  |  |  | Strategic Sites Accelerator (SSA) | 25
|  |  |  | Great British Energy | 25
|  |  |  | Mobile Fires Platform | 25

## Departmental Analysis
Department | Total Whole Life Cost £m | Red or Amber % | Project Records | Average Duration Months | Department | Total Whole Life Cost £m | Reporting Year | All
MOD | 195988.87 | 95% | 91 | 232.5603 | MOJ | 31999.22
DFT | 139441.09 | 100% | 35 | 197.1217 | DWP | 38425.49 | Delivery Rating | Project Records
HO | 135300.67 | 100% | 37 | 89.705 | DFE | 44007.75 | AMBER | 112
DESNZ | 128438.29 | 100% | 40 | 170.5654 | MHCLG | 69374.62 | GREEN | 11
DHSC | 115176.44 | 83.33% | 18 | 123.4357 | DEFRA | 83749.57 | RED | 44
DEFRA | 83749.57 | 87.5% | 23 | 107.52 | DHSC | 115176.44 | Grand Total | 167
MHCLG | 69374.62 | 90% | 21 | 122.8615 | DESNZ | 128438.29
DFE | 44007.75 |  | 18 | 86.6333 | HO | 135300.67
DWP | 38425.49 | 78.57% | 15 | 111.68 | DFT | 139441.09
MOJ | 31999.22 | 93.33% | 36 | 82.2861 | MOD | 195988.87
Grand Total | 981902.01 | 92.36% | 334 | 155.4427 | Grand Total | 981902.01
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Project Risk Register
Project Name | Department | Annual Report Category | Major Projects ID | Reporting Year | Whole Life Cost Clean | Duration Months | FY Variance Clean | IPA Rating Clean | Delivery Risk Score | Cost Exposure Score | Duration Exposure Score | Variance Risk Score | Total Risk Score | Risk Tier
ARMOURED CAVALRY 2025 | MOD | Military Capability | MOD_0091_1415-Q3 | 2025-26 | 8935.68 | 183.8 | 23.88 | RED | 40 | 25 | 20 | 15 | 100 | Critical
ARMOUR MBT 2025 | MOD | Military Capability | MOD_0104_1617-Q1 | 2025-26 | 1979.22 | 214.2 | 33.29 | RED | 40 | 20 | 20 | 15 | 95 | Critical
FARMING AND COUNTRYSIDE PROGRAMME | DEFRA | Government Transformation and Service Delivery | DEFRA_0008_2021-Q1 | 2025-26 | 25494.95 | 140 | 9.38 | RED | 40 | 25 | 20 | 5 | 90 | Critical
EAST COAST DIGITAL PROGRAMME | DFT | Infrastructure and Construction | DFT_0038_1920-Q4 | 2025-26 | 3030.39 | 161.4 | 15.88 | RED | 40 | 20 | 20 | 10 | 90 | Critical
Remediation Portfolio | MHCLG | Infrastructure and Construction | DLUHC_0250_2324-Q1 | 2025-26 | 9726.6 | 153.2 | 5.3 | RED | 40 | 25 | 20 | 5 | 90 | Critical
SUBMARINE WATERFRONT INFRASTRUCTURE FUTURE | MOD | Infrastructure and Construction | MOD_0011_2122-Q2 | 2025-26 | 2230.52 | 172.6 | 17.7 | RED | 40 | 20 | 20 | 10 | 90 | Critical
Hydrogen Allocation Round 2 (HAR2) | DESNZ | Infrastructure and Construction | DESNZ_0397_2425-Q2 | 2025-26 | 9427.02 | 216.6 |  | RED | 40 | 25 | 20 | 0 | 85 | Critical
NORTHERN POWERHOUSE RAIL | DFT | Infrastructure and Construction | DFT_0141_2223-Q1 | 2025-26 | 45000 | 430.9 | 69.79 | AMBER | 25 | 25 | 20 | 15 | 85 | Critical
NEW HOSPITAL PROGRAMME | DHSC | Infrastructure and Construction | DHSC_0066_2021-Q2 | 2025-26 | 47523.91 | 303.1 | 24.01 | AMBER | 25 | 25 | 20 | 15 | 85 | Critical
LAND ENVIRONMENT TACTICAL COMMUNICATION AND INFORMATION SYSTEMS | MOD | Military Capability | MOD_0105_1617-Q1 | 2025-26 | 7734.29 | 266.5 | 47.19 | AMBER | 25 | 25 | 20 | 15 | 85 | Critical
NEW STYLE OF INFORMATION TECHNOLOGY DEPLOYED | MOD | Information and Communications Technology (ICT) | MOD_0109_1617-Q2 | 2025-26 | 1598.79 | 168 | 2.42 | RED | 40 | 20 | 20 | 5 | 85 | Critical
MECHANISED INFANTRY PROGRAMME | MOD | Military Capability | MOD_0115_1718-Q2 | 2025-26 | 5033.66 | 190.4 | 54.27 | AMBER | 25 | 25 | 20 | 15 | 85 | Critical
GEOLOGICAL DISPOSAL FACILITY | DESNZ | Infrastructure and Construction | DECC_0005_1112-Q1 | 2025-26 | 26350.29 |  | 21.71 | RED | 40 | 25 | 0 | 15 | 80 | Critical
Law Enforcement Data Service | HO | Information and Communications Technology (ICT) | HO_0036_1617-Q2 | 2025-26 | 1086.68 | 153 | 35.18 | AMBER | 25 | 20 | 20 | 15 | 80 | Critical
COLLECTIVE TRAINING TRANSFORMATION PROGRAMME | MOD | Military Capability | MOD_0121_2021-Q4 | 2025-26 | 2083.25 | 261.9 | 23.24 | AMBER | 25 | 20 | 20 | 15 | 80 | Critical
LAND INTELLIGENCE, SURVEILLANCE, TARGET ACQUISITION AND RECONNAISSANCE (ISTAR) | MOD | Military Capability | MOD_0056_2122-Q3 | 2025-26 | 1498.14 | 171.2 | 34.54 | AMBER | 25 | 20 | 20 | 15 | 80 | Critical
GROUND BASED AIR DEFENCE (GBAD) | MOD | Military Capability | MOD_0144_2122-Q1 | 2025-26 | 1454.95 | 186 | 43.75 | AMBER | 25 | 20 | 20 | 15 | 80 | Critical
COLLECTIONS, PACKAGING AND REFORMS PROGRAMME | DEFRA | Government Transformation and Service Delivery | DEFRA_0040_2122-Q3 | 2025-26 | 5204.73 | 122 | 3.24 | AMBER | 25 | 25 | 20 | 5 | 75 | Critical
SERVICE MODERNISATION PROGRAMME | DWP | Government Transformation and Service Delivery | DWP_0217_2223-Q4 | 2025-26 | 1150 | 132 | 13.19 | AMBER | 25 | 20 | 20 | 10 | 75 | Critical
FUTURE BORDER AND IMMIGRATION SYSTEM PROGRAMME (FBIS) | HO | Government Transformation and Service Delivery | HO_0039_1920-Q4 | 2025-26 | 5140.89 | 108 | 18.09 | AMBER | 25 | 25 | 15 | 10 | 75 | Critical
FUTURE AIR DOMINANCE SYSTEM | MOD | Military Capability | MOD_0479_2425-Q4 | 2025-26 |  | 283 | 30.71 | RED | 40 | 0 | 20 | 15 | 75 | Critical
CORE PRODUCTION CAPABILITY | MOD | Military Capability | MOD_0078_1213-Q1 | 2025-26 | 7784.34 | 380.2 | 7.77 | AMBER | 25 | 25 | 20 | 5 | 75 | Critical
10K Additional Prison Places Estate Expansion Houseblocks and Refurbishments | MOJ | Infrastructure and Construction | MOJ_0113_2122-Q2 | 2025-26 |  | 137.7 | 56.9 | RED | 40 | 0 | 20 | 15 | 75 | Critical
10K Additional Prison Places Estate Expansion Category D | MOJ | Infrastructure and Construction | MOJ_0111_2122-Q2 | 2025-26 |  | 133.8 | 65.99 | RED | 40 | 0 | 20 | 15 | 75 | Critical
Warm Homes Agency | DESNZ | Government Transformation and Service Delivery | DESNZ_0542_2526-Q2 | 2025-26 | 276.69 | 41.8 | 16.77 | RED | 40 | 10 | 10 | 10 | 70 | Critical
LOWER THAMES CROSSING | DFT | Infrastructure and Construction | DFT_0022_1415-Q4 | 2025-26 | 9899.54 | 254 | 0 | AMBER | 25 | 25 | 20 | 0 | 70 | Critical
Health Transformation Programme | DWP | Government Transformation and Service Delivery | DWP_0028_1819-Q3 | 2025-26 | 735.46 | 138 | 10.98 | AMBER | 25 | 15 | 20 | 10 | 70 | Critical
Workplace Transformation | DWP | Government Transformation and Service Delivery | DWP_0013_2122-Q2 | 2025-26 | 3367.17 | 128.9 | 2.09 | AMBER | 25 | 20 | 20 | 5 | 70 | Critical
UNITY PROGRAMME | HMRC | Government Transformation and Service Delivery | HMRC_0031_2122-Q3 | 2025-26 | 245.97 | 86.9 | 0.29 | RED | 40 | 10 | 15 | 5 | 70 | Critical
MAKING TAX DIGITAL | HMRC | Information and Communications Technology (ICT) | HMRC_0017_1617-Q2 | 2025-26 | 1484.62 | 155.9 | 0.34 | AMBER | 25 | 20 | 20 | 5 | 70 | Critical
HOME OFFICE BIOMETRICS (HOB) PROGRAMME | HO | Information and Communications Technology (ICT) | HO_0033_1415-Q3 | 2025-26 | 1809.85 | 153 | 2.74 | AMBER | 25 | 20 | 20 | 5 | 70 | Critical
CLYDE INFRASTRUCTURE | MOD | Military Capability | MOD_0118_1718-Q3 | 2025-26 | 3324.98 | 198.8 | 7.43 | AMBER | 25 | 20 | 20 | 5 | 70 | Critical
SOCIAL HOUSING DECARBONISATION FUND | DESNZ | Infrastructure and Construction | BEIS_0014_2021-Q4 | 2025-26 | 2256.29 | 114.7 | 0.12 | AMBER | 25 | 20 | 15 | 5 | 65 | High
FRONTLINE DIGITISATION | DHSC | Information and Communications Technology (ICT) | DHSC_0071_2122-Q1 | 2025-26 | 2080.52 | 60 | 2.61 | AMBER | 25 | 20 | 15 | 5 | 65 | High
SYNERGY PROGRAMME | DWP | Government Transformation and Service Delivery | DWP_0042_2122-Q3 | 2025-26 | 1990.99 | 94 | 5.21 | AMBER | 25 | 20 | 15 | 5 | 65 | High
EMERGENCY SERVICES MOBILE COMMUNICATIONS | HO | Information and Communications Technology (ICT) | HO_0016_1213-Q1 | 2025-26 | 18139.58 |  | 49.93 | AMBER | 25 | 25 | 0 | 15 | 65 | High
Affordable Homes Programme (AHP) | MHCLG | Infrastructure and Construction | DLUHC_0138_2223-Q1 | 2025-26 | 12230.5 | 110.8 | 0 | AMBER | 25 | 25 | 15 | 0 | 65 | High
Electronic Monitoring Expansion | MOJ | Government Transformation and Service Delivery | MOJ_0058_2122-Q1 | 2025-26 | 1161.1 | 65.4 | 6.34 | AMBER | 25 | 20 | 15 | 5 | 65 | High
Manchester Digital Campus | CO | Infrastructure and Construction | CO_0438_2425-Q3 | 2025-26 | 1029.78 | 92.3 | 0 | AMBER | 25 | 20 | 15 | 0 | 60 | High
4th National Lottery Licence | DCMS | Government Transformation and Service Delivery | DCMS_0013_1819-Q3 | 2025-26 | 174.46 | 90.4 | 15.42 | AMBER | 25 | 10 | 15 | 10 | 60 | High
Livestock Information Transformation Programme | DEFRA | Government Transformation and Service Delivery | DEFRA_0348_2324-Q4 | 2025-26 | 525.5 |  | 2.18 | RED | 40 | 15 | 0 | 5 | 60 | High
National Biosecurity Centre (Weybridge) | DEFRA | Infrastructure and Construction | DEFRA_0007_2021-Q1 | 2025-26 | 2485.6 | 186 | 33.64 | GREEN | 5 | 20 | 20 | 15 | 60 | High
Warm Homes: Local Grant | DESNZ | Infrastructure and Construction | DESNZ_0471_2425-Q4 | 2025-26 | 454.52 | 47.9 | 37.35 | AMBER | 25 | 10 | 10 | 15 | 60 | High
GOV.UK One Login | DSIT | Government Transformation and Service Delivery | CO_0033_2122-Q1 | 2025-26 | 708.86 | 86.8 | 5.7 | AMBER | 25 | 15 | 15 | 5 | 60 | High
Enterprise Customer Relationship Management (eCRM) | HMRC | Government Transformation and Service Delivery | HMRC_0543_2526-Q2 | 2025-26 | 256.75 | 59.9 | 35.83 | AMBER | 25 | 10 | 10 | 15 | 60 | High
SKYNET 6 (AKA FBLOS) | MOD | Information and Communications Technology (ICT) | MOD_0100_1516-Q1 | 2025-26 |  | 371.9 |  | RED | 40 | 0 | 20 | 0 | 60 | High
TYPE 31 | MOD | Military Capability | MOD_0112_1718-Q1 | 2025-26 |  | 208 |  | RED | 40 | 0 | 20 | 0 | 60 | High
POST OFFICE - TRANSFORMATION | DBT | Information and Communications Technology (ICT) | DBT_0293_2324-Q3 | 2025-26 | 1553.73 |  | 15.31 | AMBER | 25 | 20 | 0 | 10 | 55 | High
EU Delivery Programme | DEFRA | Government Transformation and Service Delivery | DEFRA_0587_2526-Q3 | 2025-26 | 832.04 |  | 29.19 | AMBER | 25 | 15 | 0 | 15 | 55 | High
Flood and Coastal Risk Management (FCRM) Investment Programme 2026-2029 | DEFRA | Infrastructure and Construction |  | 2025-26 | 3861.52 | 36 |  | AMBER | 25 | 20 | 10 | 0 | 55 | High
Contact Centre as a Service (CCaaS) | HMRC | Government Transformation and Service Delivery | HMRC_0544_2526-Q2 | 2025-26 | 571.86 | 30.9 | 10.87 | AMBER | 25 | 15 | 5 | 10 | 55 | High
NEXT GENERATION (FIXED) COMMUNICATION NETWORK | MOD | Information and Communications Technology (ICT) | MOD_0126_2021-Q4 | 2025-26 |  | 106.9 |  | RED | 40 | 0 | 15 | 0 | 55 | High
Small Secure Houseblocks | MOJ | Infrastructure and Construction | MOJ_0144_2223-Q2 | 2025-26 |  | 83.4 | 30.23 | AMBER | 25 | 0 | 15 | 15 | 55 | High
Rapid Deployment Cells Project | MOJ | Infrastructure and Construction | MOJ_0057_2122-Q1 | 2025-26 |  | 84.1 | 28.85 | AMBER | 25 | 0 | 15 | 15 | 55 | High
Accelerated Houseblocks | MOJ | Infrastructure and Construction | MOJ_0053_2021-Q4 | 2025-26 |  | 121.1 | 16.07 | AMBER | 25 | 0 | 20 | 10 | 55 | High
VOA NextGen Rating Programme | VOA | Government Transformation and Service Delivery | HMRC_0143_2223-Q2 | 2025-26 | 300.38 | 66 | 5.53 | AMBER | 25 | 10 | 15 | 5 | 55 | High
Spherical Tokamak for Energy Production | DESNZ | Infrastructure and Construction | BEIS_0153_2223-Q2 | 2025-26 |  | 320.5 | 0.63 | AMBER | 25 | 0 | 20 | 5 | 50 | High
PENSIONS DASHBOARD PROGRAMME | DWP | Information and Communications Technology (ICT) | DWP_0029_2021-Q4 | 2025-26 |  | 96 | 11.19 | AMBER | 25 | 0 | 15 | 10 | 50 | High
Police National Database (PND) | HO | Information and Communications Technology (ICT) | HO_0331_2324-Q4 | 2025-26 | 282.64 |  | 74.22 | AMBER | 25 | 10 | 0 | 15 | 50 | High
MODNET EVOLVE | MOD | Information and Communications Technology (ICT) | MOD_0110_1718-Q1 | 2025-26 | 309.19 | 125 | 38.37 | GREEN | 5 | 10 | 20 | 15 | 50 | High
MENSA | MOD | Military Capability | MOD_0132_2122-Q1 | 2025-26 | 3555.91 |  | 2.6 | AMBER | 25 | 20 | 0 | 5 | 50 | High
10k Additional Prison Places - New Build | MOJ | Infrastructure and Construction | MOJ_0050_2021-Q1 | 2025-26 |  | 146.9 | 2.38 | AMBER | 25 | 0 | 20 | 5 | 50 | High
EURO 2028 | DCMS | Government Transformation and Service Delivery | DCMS_0321_2324-Q3 | 2025-26 | 511.63 |  | 2.05 | AMBER | 25 | 15 | 0 | 5 | 45 | Medium
FLOOD AND COASTAL EROSION RISK MANAGEMENT | DEFRA | Infrastructure and Construction | DEFRA_0236_2324-Q1 | 2025-26 | 4835.25 | 71.9 | 1.8 | GREEN | 5 | 20 | 15 | 5 | 45 | Medium
NATURE FOR CLIMATE FUND | DEFRA | Infrastructure and Construction | DEFRA_0013_2021-Q4 | 2025-26 | 1272.06 |  | 0 | AMBER | 25 | 20 | 0 | 0 | 45 | Medium
PUBLIC OWNERSHIP TRANSITION PROGRAMME | DFT | Government Transformation and Service Delivery | DFT_0439_2425-Q3 | 2025-26 | 36.6 | 36.9 | 9.81 | AMBER | 25 | 5 | 10 | 5 | 45 | Medium
ASYLUM TRANSFORMATION PROGRAMME | HO | Government Transformation and Service Delivery | HO_0183_2223-Q3 | 2025-26 | 429.95 |  | 16.1 | AMBER | 25 | 10 | 0 | 10 | 45 | Medium
SUBMERSIBLE SHIP NUCLEAR AUKUS | MOD | Military Capability | MOD_0007_2122-Q2 | 2025-26 |  | 348.9 |  | AMBER | 25 | 0 | 20 | 0 | 45 | Medium
FUTURE COMBAT AIR SYSTEM | MOD | Military Capability | MOD_0122_2021-Q4 | 2025-26 |  |  | 4.65 | RED | 40 | 0 | 0 | 5 | 45 | Medium
HS2 PHASE I | DFT | Infrastructure and Construction | DFT_0040_2021-Q1 | 2025-26 |  |  | 0 | RED | 40 | 0 | 0 | 0 | 40 | Medium
Rail Reform: Stand-Up of GBR | DFT | Government Transformation and Service Delivery | DFT_0413_2425-Q2 | 2025-26 |  |  |  | RED | 40 | 0 | 0 | 0 | 40 | Medium
NS&I Transformation | HMT | Government Transformation and Service Delivery | HMT_0004_2021-Q2 | 2025-26 |  |  |  | RED | 40 | 0 | 0 | 0 | 40 | Medium
Asylum Support Accommodation Programme | HO | Government Transformation and Service Delivery | HO_0286_2324-Q2 | 2025-26 |  |  |  | RED | 40 | 0 | 0 | 0 | 40 | Medium
ASYLUM ACCOMMODATION PROGRAMME (AAP) | HO | Government Transformation and Service Delivery | HO_0149_2223-Q2 | 2025-26 |  |  |  | RED | 40 | 0 | 0 | 0 | 40 | Medium
INTEGRATED SINGLE FINANCIAL ENVIRONMENT | DHSC | Information and Communications Technology (ICT) | DHSC_0067_2021-Q3 | 2025-26 | 187.99 | 92 | 0.97 | GREEN | 5 | 10 | 15 | 5 | 35 | Medium
DIGITAL PLANNING PROGRAMME | MHCLG | Government Transformation and Service Delivery | DLUHC_0181_2223-Q3 | 2025-26 | 218.54 |  | 0 | AMBER | 25 | 10 | 0 | 0 | 35 | Medium
Early Years Childcare Reform Programme | DFE | Government Transformation and Service Delivery | DFE_0272_2324-Q2 | 2025-26 | 16207.65 |  | 0 | GREEN | 5 | 25 | 0 | 0 | 30 | Medium
Connect to Work | DWP | Government Transformation and Service Delivery | DWP_0304_2324-Q3 | 2025-26 | 1094.99 |  | 1.47 | GREEN | 5 | 20 | 0 | 5 | 30 | Medium
Strategic Sites Accelerator (SSA) | DBT | Infrastructure and Construction | DBT_0296_2526-Q2 | 2025-26 |  |  |  | AMBER | 25 | 0 | 0 | 0 | 25 | Low
Great British Energy | DESNZ | Infrastructure and Construction | DESNZ_0472_2425-Q4 | 2025-26 |  |  |  | AMBER | 25 | 0 | 0 | 0 | 25 | Low
Mobile Fires Platform | MOD | Military Capability | MOD_0527_2526-Q1 | 2025-26 |  |  |  | AMBER | 25 | 0 | 0 | 0 | 25 | Low
Falcon Programme | CO | Government Transformation and Service Delivery | CO_0176_2223-Q3 | 2025-26 | 23.11 | 56 | 41.38 |  |  | 5 | 10 | 15 |  | Not scored
Future Service Programme | CO | Information and Communications Technology (ICT) | CO_0027_2021-Q4 | 2025-26 |  | 75 |  |  |  | 0 | 15 | 0 |  | Not scored
Transforming Public Procurement | CO | Government Transformation and Service Delivery | CO_0120_2223-Q1 | 2025-26 | 32.47 | 62.9 | 31.96 |  |  | 5 | 15 | 15 |  | Not scored
Drive 35 | DBT | Infrastructure and Construction | DBT_0295_2526-Q2 | 2025-26 | 1841.78 |  | 5.18 |  |  | 20 | 0 | 5 |  | Not scored
AUTOMOTIVE TRANSFORMATION FUND (ATF) | DBT | Infrastructure and Construction | BEIS_0090_2122-Q4 | 2025-26 | 702.72 |  | 82.68 |  |  | 15 | 0 | 15 |  | Not scored
British Museum - Energy Centre Programme (ECP) | DCMS | Infrastructure and Construction | DCMS_0254_2324-Q1 | 2025-26 | 181.97 | 93 | 0 |  |  | 10 | 15 | 0 |  | Not scored
Youth Investment Fund | DCMS | Infrastructure and Construction | DCMS_0118_2223-Q1 | 2025-26 | 360.15 |  | 5.71 |  |  | 10 | 0 | 5 |  | Not scored
Natural History Museum Unlocked | DCMS | Infrastructure and Construction | DCMS_0018_2021-Q3 | 2025-26 | 213.15 |  | 0.14 |  |  | 10 | 0 | 5 |  | Not scored
NORTHERN IRELAND | DEFRA | Government Transformation and Service Delivery | DEFRA_0015_2122-Q1 | 2025-26 | 430.55 | 61.3 | 9.92 |  |  | 10 | 15 | 5 |  | Not scored
NO2 PROGRAMME | DEFRA | Infrastructure and Construction | DEFRA_0014_2021-Q4 | 2025-26 | 843.04 | 122.9 | 16.52 |  |  | 15 | 20 | 10 |  | Not scored
TERRESTRIAL NATURAL CAPITAL ECOSYSTEM ASSESSMENT | DEFRA | Government Transformation and Service Delivery | DEFRA_0190_2223-Q3 | 2025-26 | 325.68 | 96 | 1.5 |  |  | 10 | 15 | 5 |  | Not scored
Cefas Infrastructure to Support Future Delivery at Sea | DEFRA | Government Transformation and Service Delivery | DEFRA_0349_2324-Q4 | 2025-26 | 152.89 |  |  |  |  | 10 | 0 | 0 |  | Not scored
Boiler Upgrade Scheme | DESNZ | Infrastructure and Construction | DESNZ_0375_2425-Q1 | 2025-26 | 3054.03 |  | 17.86 |  |  | 20 | 0 | 10 |  | Not scored
SELLAFIELD PRODUCT AND RESIDUE STORE RETREATMENT PLANT PROJECT | DESNZ | Infrastructure and Construction | BEIS_0008_2021-Q3 | 2025-26 | 1432.89 | 231.7 | 11.32 |  |  | 20 | 20 | 10 |  | Not scored
Review of Electricity Market Arrangements (REMA) | DESNZ | Government Transformation and Service Delivery | DESNZ_0333_2324-Q4 | 2025-26 | 29.18 | 26.8 | 53.38 |  |  | 5 | 5 | 15 |  | Not scored
GREEN HEAT NETWORK FUND | DESNZ | Infrastructure and Construction | BEIS_0115_2223-Q1 | 2025-26 | 730.01 | 96.7 | 1.54 |  |  | 15 | 15 | 5 |  | Not scored
HyNet Cluster | DESNZ | Infrastructure and Construction | DESNZ_0457_2425-Q3 | 2025-26 | [5 empty] | 0 | 0 | 0 |  | Not scored
GBE-N SMR Programme | DESNZ | Infrastructure and Construction | BEIS_0233_2223-Q4 | 2025-26 | [5 empty] | 0 | 0 | 0 |  | Not scored
Sizewell C Project | DESNZ | Infrastructure and Construction | BEIS_0019_2122-Q1 | 2025-26 | [5 empty] | 0 | 0 | 0 |  | Not scored
Hydrogen Allocation Round 1 (HAR1) | DESNZ | Infrastructure and Construction | DESNZ_0334_2324-Q3 | 2025-26 | 2461.71 | 239.3 | 90.33 |  |  | 20 | 20 | 15 |  | Not scored
East Coast Cluster (ECC) | DESNZ | Infrastructure and Construction | DESNZ_0458_2425-Q3 | 2025-26 | [5 empty] | 0 | 0 | 0 |  | Not scored
PUBLIC SECTOR DECARBONISATION SCHEME | DESNZ | Infrastructure and Construction | BEIS_0013_2021-Q4 | 2025-26 | 3759 | 92.7 | 7.72 |  |  | 20 | 15 | 5 |  | Not scored
BEPPS2 | DESNZ | Infrastructure and Construction | BEIS_0241_2324-Q1 | 2025-26 | 727.6 | 211.9 | 1.45 |  |  | 15 | 20 | 5 |  | Not scored
SIXEP CONTINUITY PLANT | DESNZ | Infrastructure and Construction | BEIS_0009_2021-Q3 | 2025-26 | 1097.5 | 220.9 | 23.84 |  |  | 20 | 20 | 15 |  | Not scored
Smart Metering Implementation Programme | DESNZ | Infrastructure and Construction | DECC_0010_1112-Q1 | 2025-26 | 20176.55 | 252.9 |  |  |  | 25 | 20 | 0 |  | Not scored
T-Levels | DFE | Government Transformation and Service Delivery | DFE_0010_1819-Q1 | 2025-26 | 2025 | 142.2 | 10.96 |  |  | 20 | 20 | 10 |  | Not scored
Families First Partnership Programme | DFE | Government Transformation and Service Delivery | DFT_0498_2526-Q2 | 2025-26 | 2922.61 | 48 | 3.7 |  |  | 20 | 10 | 5 |  | Not scored
School Rebuilding Programme | DFE | Infrastructure and Construction | DFE_0018_2021-Q3 | 2025-26 | [5 empty] | 0 | 0 | 0 |  | Not scored
School-based nurseries | DFE | Infrastructure and Construction | DFE_0496_2526-Q1 | 2025-26 | 369.85 | 61.9 | 9.19 |  |  | 10 | 15 | 5 |  | Not scored
Free Breakfast Clubs | DFE | Government Transformation and Service Delivery | DFE_0495_2526-Q1 | 2025-26 | [5 empty] | 0 | 0 | 0 |  | Not scored
FE Capital Transformation | DFE | Infrastructure and Construction | DFE_0015_2021-Q3 | 2025-26 | 2057.2 | 114 | 0.66 |  |  | 20 | 15 | 5 |  | Not scored
Lifelong Learning Entitlement | DFE | Government Transformation and Service Delivery | DFE_0109_2223-Q1 | 2025-26 | [5 empty] | 0 | 0 | 0 |  | Not scored
Children's Homes Capital Programme | DFE | Infrastructure and Construction |  | 2025-26 | 610.13 |  | 0 |  |  | 15 | 0 | 0 |  | Not scored
2ND GENERATION UK SEARCH AND RESCUE AVIATION | DFT | Government Transformation and Service Delivery | DFT_0048_2021-Q3 | 2025-26 | 2046.47 | 84.5 | 5.04 |  |  | 20 | 15 | 5 |  | Not scored
EAST WEST RAIL CONNECTION STATE 1 | DFT | Infrastructure and Construction | DFT_0046_2021-Q2 | 2025-26 |  |  | 19.9 |  |  | 0 | 0 | 10 |  | Not scored
REDEVELOPMENT EUSTON CONVENTIONAL STATION (RECS) | DFT | Infrastructure and Construction | DFT_0139_2223-Q1 | 2025-26 |  |  | 0 |  |  | 0 | 0 | 0 |  | Not scored
EAST COAST MAINLINE PROGRAMME | DFT | Infrastructure and Construction | DFT_0033_1819-Q1 | 2025-26 | 1276.49 | 157 |  |  |  | 20 | 20 | 0 |  | Not scored
A428 BLACK CAT TO CAXTON GIBBET | DFT | Infrastructure and Construction | DFT_0031_1819-Q1 | 2025-26 |  |  | 3.98 |  |  | 0 | 0 | 5 |  | Not scored
A66 Northern Trans-Pennine | DFT | Infrastructure and Construction | DFT_0047_2021-Q3 | 2025-26 |  | 111.9 | 0 |  |  | 0 | 15 | 0 |  | Not scored
EAST WEST RAIL CONNECTION STATE 2 AND 3 | DFT | Infrastructure and Construction | DFT_0052_2122-Q1 | 2025-26 |  | 281 | 4.89 |  |  | 0 | 20 | 5 |  | Not scored
A417 AIR BALLOON | DFT | Infrastructure and Construction | DFT_0044_2021-Q2 | 2025-26 | 542.63 | 149 | 6.8 |  |  | 15 | 20 | 5 |  | Not scored
MIDLANDS RAIL HUB | DFT | Infrastructure and Construction | DFT_0043_2021-Q2 | 2025-26 | 948.37 | 285 | 0 |  |  | 15 | 20 | 0 |  | Not scored
TRANSPENNINE ROUTE UPGRADE | DFT | Infrastructure and Construction | DFT_0037_1920-Q3 | 2025-26 | 10658.6 | 291.5 | 0.18 |  |  | 25 | 20 | 5 |  | Not scored
UK Health Security Campus | DHSC | Infrastructure and Construction | DOH_0017_1112-Q1 | 2025-26 | [5 empty] | 0 | 0 | 0 |  | Not scored
NHS Digital Transformation of Screening | DHSC | Government Transformation and Service Delivery | DHSC_0069_2021-Q4 | 2025-26 | 94.5 | 131.9 | 11.46 |  |  | 5 | 20 | 10 |  | Not scored
Future NHS Workforce Solution Transformation Programme | DHSC | Information and Communications Technology (ICT) | DHSC_0041_2122-Q3 | 2025-26 |  | 133.9 |  |  |  | 0 | 20 | 0 |  | Not scored
MODERNA STRATEGIC PARTNERSHIP PROGRAMME | DHSC | Government Transformation and Service Delivery | DHSC_0243_2324-Q1 | 2025-26 | [5 empty] | 0 | 0 | 0 |  | Not scored
FEDERATED DATA PLATFORM | DHSC | Government Transformation and Service Delivery | DHSC_0252_2324-Q1 | 2025-26 | 1084.31 | 120 | 0.71 |  |  | 20 | 20 | 5 |  | Not scored
Met Office Supercomputer Programme | DSIT | Information and Communications Technology (ICT) | BEIS_0005_1920-Q4 | 2025-26 | 1204.33 | 174.3 | 11.68 |  |  | 20 | 20 | 10 |  | Not scored
Project Gigabit | DSIT | Infrastructure and Construction | DCMS_0019_2021-Q4 | 2025-26 | 5214.96 | 141 | 29.11 |  |  | 25 | 20 | 15 |  | Not scored
Shared Rural Network | DSIT | Infrastructure and Construction | DCMS_0020_2122-Q1 | 2025-26 | 328.19 | 251.1 | 24.62 |  |  | 10 | 20 | 15 |  | Not scored
MATRIX CLUSTER TRANSFORMATION PROGRAMME | DSIT | Government Transformation and Service Delivery | BEIS_0079_2122-Q4 | 2025-26 | 889.81 | 67.9 | 5.38 |  |  | 15 | 15 | 5 |  | Not scored
Skills Bootcamps | DWP | Government Transformation and Service Delivery | DFE_0017_2021-Q3 | 2025-26 | 790.39 |  | 62.08 |  |  | 15 | 0 | 15 |  | Not scored
TOKYO NEW BUILD, REMODELLING AND REFURBISHMENT | FCDO | Infrastructure and Construction | FCO_0216_2223-Q4 | 2025-26 | 111.25 |  | 49.57 |  |  | 10 | 0 | 15 |  | Not scored
LOCAL LAND CHARGES (LLC) PROGRAMME | HMLR | Government Transformation and Service Delivery | BIS_0015_1516-Q1 | 2025-26 | 346.22 | 178 | 6.41 |  |  | 10 | 20 | 5 |  | Not scored
ENTERPRISE TAX MANAGEMENT PLATFORM (ETMP) | HMRC | Government Transformation and Service Delivery | HMRC_0292_2324-Q3 | 2025-26 | 480.87 | 94.1 | 12.61 |  |  | 10 | 15 | 10 |  | Not scored
HMRC NORTHERN IRELAND DELIVERY PROGRAMME | HMRC | Information and Communications Technology (ICT) | HMRC_0164_2223-Q3 | 2025-26 | 712.9 | 60 | 0 |  |  | 15 | 15 | 0 |  | Not scored
BUILDING OUR FUTURE LOCATIONS PROGRAMME | HMRC | Government Transformation and Service Delivery | HMRC_0015_1617-Q1 | 2025-26 | 2831.53 | 183 | 5.31 |  |  | 20 | 20 | 5 |  | Not scored
NATIONAL STRATEGIC AUTOMATIC NUMBER PLATE RECOGNITION PLATFORM (NSAP) | HO | Government Transformation and Service Delivery | HO_0332_2324-Q4 | 2025-26 | 391.77 | 85 | 5.91 |  |  | 10 | 15 | 5 |  | Not scored
MARITIME CAPABILITIES REPLACEMENT PROGRAMME | HO | Government Transformation and Service Delivery | HO_0150_2223-Q2 | 2025-26 | [5 empty] | 0 | 0 | 0 |  | Not scored
Civil Registration Service Transformation (CReST) | HO | Government Transformation and Service Delivery | HO_0373_2425-Q1 | 2025-26 | 326.85 |  | 24.37 |  |  | 10 | 0 | 15 |  | Not scored
FRAUD AND CYBER CRIME REPORTING AND ANALYSIS SERVICE | HO | Government Transformation and Service Delivery | HO_0045_2122-Q1 | 2025-26 | 169.06 |  | 0 |  |  | 10 | 0 | 0 |  | Not scored
RADIOLOGICAL AND NUCLEAR CHANGE PROGRAMME (RNCP) | HO | Government Transformation and Service Delivery | HO_0047_2122-Q1 | 2025-26 | [5 empty] | 0 | 0 | 0 |  | Not scored
Immigration Removal Centre (IRC) Expansion Programme | HO | Infrastructure and Construction | HO_0330_2324-Q4 | 2025-26 | [5 empty] | 0 | 0 | 0 |  | Not scored
Cerberus | HO | Government Transformation and Service Delivery | HO_0042_2021-Q3 | 2025-26 | 285.1 | 123 | 3.41 |  |  | 10 | 20 | 5 |  | Not scored
ANTI-MONEY LAUNDERING AND ASSET RECOVERY (AMLAR) | HO | Government Transformation and Service Delivery | HO_0228_2223-Q4 | 2025-26 | 368.47 |  | 8.89 |  |  | 10 | 0 | 5 |  | Not scored
Levelling Up Home Building Fund | MHCLG | Infrastructure and Construction | DLUHC_0135_2223-Q1 | 2025-26 | 1990.98 | 136.1 | 17.49 |  |  | 20 | 20 | 10 |  | Not scored
GRENFELL SITE AND PROGRAMME | MHCLG | Infrastructure and Construction | MHCLG_0001_1920-Q3 | 2025-26 | [5 empty] | 0 | 0 | 0 |  | Not scored
HOUSING INFRASTRUCTURE FUND | MHCLG | Infrastructure and Construction | MHCLG_0004_2021-Q4 | 2025-26 | 4250.15 | 135 | 8.96 |  |  | 20 | 20 | 5 |  | Not scored
Brownfield, Infrastructure & Land (BIL) | MHCLG | Infrastructure and Construction | DLUHC_0364_2324-Q4 | 2025-26 | 1506.89 | 93 | 0 |  |  | 20 | 15 | 0 |  | Not scored
Freeports | MHCLG | Infrastructure and Construction | MHCLG_0008_2122-Q1 | 2025-26 | 378.33 | 133.8 | 0 |  |  | 10 | 20 | 0 |  | Not scored
UK HOLOCAUST MEMORIAL AND LEARNING CENTRE | MHCLG | Infrastructure and Construction | MHCLG_0005_2021-Q4 | 2025-26 | 141.87 |  | 55.21 |  |  | 10 | 0 | 15 |  | Not scored
FUTURE CRUISE ANTI SHIP WEAPON (FCASW) | MOD | Military Capability | MOD_0139_2122-Q1 | 2025-26 |  | 631.9 |  |  |  | 0 | 20 | 0 |  | Not scored
PROTECTOR | MOD | Military Capability | MOD_0107_1617-Q1 | 2025-26 | 1732.77 | 254 | 33.4 |  |  | 20 | 20 | 15 |  | Not scored
MULTI ROLE STRIKE SHIP | MOD | Military Capability | MOD_0320_2324-Q3 | 2025-26 |  | 190 |  |  |  | 0 | 20 | 0 |  | Not scored
TYPE 26 GLOBAL COMBAT SHIP PROGRAMME | MOD | Military Capability | MOD_0055_1112-Q1 | 2025-26 |  | 342.3 |  |  |  | 0 | 20 | 0 |  | Not scored
ASTUTE BOATS 1-7 | MOD | Military Capability | MOD_0076_1213-Q1 | 2025-26 | 14428.06 |  |  |  |  | 25 | 0 | 0 |  | Not scored
DREADNOUGHT | MOD | Military Capability | MOD_0080_1213-Q1 | 2025-26 | [5 empty] | 0 | 0 | 0 |  | Not scored
BRIMSTONE 3 | MOD | Military Capability | MOD_0141_2122-Q1 | 2025-26 |  | 166.3 |  |  |  | 0 | 20 | 0 |  | Not scored
TEUTATES | MOD | Military Capability | MOD_0134_2122-Q1 | 2025-26 |  | 207 |  |  |  | 0 | 20 | 0 |  | Not scored
SPEARFISH UPGRADE PROGRAMME | MOD | Military Capability | MOD_0047_1112-Q1 | 2025-26 | [5 empty] | 0 | 0 | 0 |  | Not scored
ARMED FORCES RECRUITING PROGRAMME | MOD | Military Capability | MOD_0119_1920-Q2 | 2025-26 | 201.02 | 121.5 | 16.24 |  |  | 10 | 20 | 10 |  | Not scored
Future Materials Campus | MOD | Military Capability | MOD_0247_2324-Q1 | 2025-26 |  |  | 9.19 |  |  | 0 | 0 | 5 |  | Not scored
DEFENCE ESTATE OPTIMISATION | MOD | Military Capability | MOD_0114_1718-Q1 | 2025-26 | 5949.19 | 294 | 47.58 |  |  | 25 | 20 | 15 |  | Not scored
MARSHALL | MOD | Military Capability | MOD_0033_1112-Q1 | 2025-26 | 1997.56 | 246.9 | 35.46 |  |  | 20 | 20 | 15 |  | Not scored
SPEARCAP 3 | MOD | Military Capability | MOD_0140_2122-Q1 | 2025-26 |  | 327 |  |  |  | 0 | 20 | 0 |  | Not scored
FLEET SOLID SUPPORT | MOD | Military Capability | MOD_0116_1718-Q2 | 2025-26 |  | 208.4 | 17.02 |  |  | 0 | 20 | 10 |  | Not scored
EUROPEAN COMMON RADAR SYSTEM MK 2 | MOD | Military Capability | MOD_0137_2122-Q1 | 2025-26 | 2899.01 | 190.9 | 15.13 |  |  | 20 | 20 | 10 |  | Not scored
E7 WEDGETAIL | MOD | Military Capability | MOD_0120_2021-Q2 | 2025-26 | 2128.05 | 145.8 | 52.85 |  |  | 20 | 20 | 15 |  | Not scored
CHINOOK CAPABILITY SUSTAINMENT PROGRAMME (CSP) | MOD | Military Capability | MOD_0009_2122-Q2 | 2025-26 | 1959.31 | 163 | 20.24 |  |  | 20 | 20 | 15 |  | Not scored
LIGHTNING PROGRAMME | MOD | Military Capability | MOD_0079_1213-Q1 | 2025-26 |  | 293.9 |  |  |  | 0 | 20 | 0 |  | Not scored
MINE HUNTING CAPABILITY | MOD | Military Capability | MOD_0124_2021-Q4 | 2025-26 |  | 233.9 |  |  |  | 0 | 20 | 0 |  | Not scored
JOINT CRYPT KEY PROGRAMME | MOD | Information and Communications Technology (ICT) | MOD_0111_1718-Q1 | 2025-26 | [5 empty] | 0 | 0 | 0 |  | Not scored
NAVAL SUPPORT INTEGRATED GLOBAL NETWORK (NSIGN) | MOD | Military Capability | MOD_0136_2122-Q1 | 2025-26 | 14352.16 | 96.9 |  |  |  | 25 | 15 | 0 |  | Not scored
NEW MEDIUM HELICOPTER | MOD | Military Capability | MOD_0125_2021-Q4 | 2025-26 | 1404.92 | 193 | 13.57 |  |  | 20 | 20 | 10 |  | Not scored
SUBMARINE DISMANTLING PROJECT | MOD | Military Capability | MOD_0135_2122-Q1 | 2025-26 | 541.73 | 187.1 | 16.06 |  |  | 15 | 20 | 10 |  | Not scored
Evolve: WAN/LAN (Networks) | MOJ | Information and Communications Technology (ICT) | MOJ_0050_2122-Q3 | 2025-26 | 253.89 | 86.6 | 78.81 |  |  | 10 | 15 | 15 |  | Not scored
Community Support Programme | MOJ | Government Transformation and Service Delivery | MOJ_0537_2526-Q1 | 2025-26 | 1024.83 | 72.3 | 0 |  |  | 20 | 15 | 0 |  | Not scored
Decommission and Legacy Risk Migration (DLRM) | MOJ | Information and Communications Technology (ICT) | MOJ_0061_2122-Q3 | 2025-26 | 273.28 | 87 | 19.12 |  |  | 10 | 15 | 10 |  | Not scored
Evolve: End User Computer Service (EUCS) | MOJ | Information and Communications Technology (ICT) | MOJ_0062_2122-Q3 | 2025-26 | 190.18 | 60.6 | 37.88 |  |  | 10 | 15 | 15 |  | Not scored
Prisoner Education Services | MOJ | Government Transformation and Service Delivery | MOJ_0064_2122-Q3 | 2025-26 | 1755.13 | 70 | 3.85 |  |  | 20 | 15 | 5 |  | Not scored
Property Transformation Programme | MOJ | Government Transformation and Service Delivery | MOJ_0220_2223-Q4 | 2025-26 |  | 71.9 |  |  |  | 0 | 15 | 0 |  | Not scored
Evolve: Voice & Video | MOJ | Information and Communications Technology (ICT) | MOJ_0049_2122-Q3 | 2025-26 | 184.56 | 81.5 | 45.34 |  |  | 10 | 15 | 15 |  | Not scored
PFI Prison Expiry and Transfer Tranche 2 | MOJ | Government Transformation and Service Delivery | MOJ_0060_2122-Q3 | 2025-26 | 2730.04 | 54.2 | 3 |  |  | 20 | 10 | 5 |  | Not scored
Secure Children's Homes Commissioning | MOJ | Government Transformation and Service Delivery | MOJ_0259_2324-Q1 | 2025-26 | 270.91 | 45.1 | 4.83 |  |  | 10 | 10 | 5 |  | Not scored
Residential Property Tribunal | MOJ | Government Transformation and Service Delivery | MOJ_0539_2526-Q2 | 2025-26 | 149.6 | 45.6 | 78.84 |  |  | 10 | 10 | 15 |  | Not scored
PFI Prison Expiry and Transfer Tranche 3 | MOJ | Government Transformation and Service Delivery | MOJ_0365_2425-Q1 | 2025-26 | 3335.69 | 79.5 | 82.16 |  |  | 20 | 15 | 15 |  | Not scored
Concordis | NCA | Government Transformation and Service Delivery | HO_0526_2526-Q1 | 2025-26 | 189.75 |  | 0 |  |  | 10 | 0 | 0 |  | Not scored

## Risk Summary
Risk scoring combines delivery confidence, whole-life cost exposure, project duration and financial-year variance.
| Risk Tier | Project Count | Total Whole-Life Cost £m | Average Risk Score | Risk Tier | Count of Project Name
| Critical | 32 | 240612.58 | 79.6875 | Critical | 32
| High | 30 | 54761.72 | 57.5 | High | 30
| Medium | 16 | 24794.66 | 40.3125 | Medium | 16
| Low | 3 |  | 25 | Low | 3
| Not scored | 108 | 143883.7 |  | Grand Total | 81
| Grand Total | 189 | 464052.66 | 61.6667
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Data Quality
Portfolio Validation
Confirms record counts, rating distribution and whole-life cost totals after refresh.
Reporting Year | Count of Project Name | Sum of Whole Life Cost Clean | Reporting Year | Project Records | Missing Cost Projects | Missing Duration Projects | Unrated Projects | Cost Data Coverage % | Duration Data Coverage %
2024-25 | 213 | 565707.28 | 2024-25 | 213 | 56 | 59 | 127 | 73.71% | 72.3%
AMBER | 61 | 213382.35 | 2025-26 | 189 | 56 | 57 | 108 | 70.37% | 69.84%
GREEN | 5 | 20339.06 | Grand Total | 402 | 112 | 116 | 235 | 72.14% | 71.14%
RED | 20 | 102862.12
(blank) | 127 | 229123.75
2025-26 | 189 | 464052.66
AMBER | 51 | 205226.67
GREEN | 6 | 25120.67
RED | 24 | 89821.62
(blank) | 108 | 143883.7
Grand Total | 402 | 1029759.94

## Methodology
Methodology and Assumptions
UK Government Major Projects ¦ Cost, Schedule and Delivery-Risk Dashboard
1. Purpose
This workbook analyses UK Government Major Projects across the 2024–25 and 2025–26 reporting periods. It compares project cost, duration, departmental responsibility and delivery-confidence ratings, and applies a custom analytical risk score to support portfolio-level prioritisation.
2. Data Sources
Item | Description
Source | NISTA Major Projects Annual Report dataset
Reporting Periods | 2024–25 and 2025–26
Grain | One row per project per reporting period
Cost unit | £ millions, presented in 2024–25 real prices
Refresh method | Power Query
Analytical model | Excel Data Model and Power Pivot
Original text fields are retained where the source contains exemptions, planning-stage notes or ranges. Separate cleaned numeric and date fields are used for analysis.
3. Data Preparation Rules
Field | Cleaning rule
Department | Trimmed, cleaned and standardised to uppercase for relationships
Reporting Year | Added during Power Query import
Start Date | Valid UK-format dates converted; other text becomes null
End Date | Valid UK-format dates converted; ranges may remain unavailable
Duration Months | Days between clean start and end dates divided by 30.44
Whole-Life Cost | Numeric values retained; midpoint used for Low/Mid/High ranges
Benefits | Numeric values retained; midpoint used where a range is supplied
IPA Rating | Standardised to RED, AMBER or GREEN
Missing/exempt values | Retained in original fields and represented as null analytically
4. Analytical Risk Score
The risk score is an independently developed analytical indicator. It is not an official NISTA or departmental project rating.
Component | Rule | Points
Delivery confidence | Green | 5
| Amber | 25
| Red | 40
Cost exposure | Under £100m | 5
| £100m–£500m | 10
| £500m–£1bn | 15
| £1bn–£5bn | 20
| £5bn+ | 25
Duration exposure | Under 3 years | 5
| 3–5 years | 10
| 5–10 years | 15
| 10+ years | 20
Financial variance | 0% or lower | 0
| Above 0% | 5
| 10% or above | 10
| 20% or above | 15
Maximum possible score: 100
5. Risk Tier Thresholds
Risk Tier | Total Risk Score | Interpretation
Critical | 70–100 | Highest analytical exposure
High | 50–69 | Elevated analytical exposure
Medium | 30–49 | Moderate analytical exposure
Low | Below 30 | Lower analytical exposure
Not scored | No usable IPA rating | No total analytical risk score assigned
6. Assumptions and Limitations
1.A high-value or long-duration project is not necessarily poorly managed; these factors represent exposure, not failure.
2.The financial variance field represents the reported financial-year position, not necessarily whole-life cost overruns.
3.Projects without a usable IPA rating are not assigned a total analytical risk score.
4.Midpoint values are used where Low/Mid/High cost ranges are reported.
5.Missing dates reduce the number of projects included in duration analysis.
6.Comparisons between years may reflect projects entering or leaving the portfolio, as well as changes to existing projects.
7.Department names were standardised for modelling consistency.
8.The model should support prioritisation and investigation, not replace detailed project assurance.
To refresh the workbook, replace or add annual source files using the established naming and column-standardisation rules, then select Data → Refresh All.